## Sheet1
Generalized Timeline for Reach Code Development and Adoption
Task | MONTH
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Develop idea for draft ordinance
Obtain cost-effectiveness study
Work with stakeholders
Develop & draft ordinance
Review by local committees
Public process & revisions
First reading of ordinance (introduction)
Second reading of ordinance (adoption)
Application to CEC
CEC review & comment period (15 days
Approval from CEC at business mtg
File with BSC
Reach code takes effect